## Pilot Projects
RJ COUNCIL ACTION PLANNING WORKSHEET
WORKGROUP: | Pilot Projects
CHAIR: | Meg Williams
MEMBERS: | Gabrielle, Alice, | Peggy, Esther (not present at meeting)
Activity Task | Responsible Party | Projected Timeline | Completion Date | Outcomes | Communication | Next Steps | Notes | Updates from Meeting
Establish Learning Communities among Pilots |  | ongoing | ongoing | Connections and communication between pilots is good. 3/4 share info and forms. | In progress | create a list serve for them to have easier communication | Deb has already begun this process with the pilot implementation teams. | The pilots contiue to work as a learning community. There are various challenges in each district and those are often addressed at the cohort meetings helpd quarterly. The next one is Aug 15th
Develop Information gathering doc for pilot project for this FY (may be used for next FY too) | Deb | complete | Done | sent to pilots for completion by March 7th | committee approved | Meg will send the DCJ Diversion app as a template. The group will talk about this on Feb 21st at the Implemenation team meeting. | Include: population to be served, demographics, case types, estimated #s, fees, who will collect fees, how will funds be distributed/used, sliding scale, inkind support, district support, other $upport, what services will be provided and by whom, who are community providers, how will data be collected, by whom, capacity to use the state database, budget,
Develop Application Process & Guidelines for FY '16 | Committee | 2014-12-30 | 2014-12-30 | prepared to open for funding apps |  | this is underway as FY '15 process gets refined | the pilot app is template for this work
Data Collection |  |  | ongoing | cloud-based data collection system to be used by all pilot sites | Omni continues to work with pilots | Work with pilots to ensure we have all useful data points. Work with database developer to ensure we have useable design | Omni lead this using ETO DB used in Diversion. | Data collection will happen for FY '14 using paper form Meg created
Develop Funding/Budget form | Committee |  | complete
Identify legislative fixes | Committee in partnership with legislative committee | June 30 2014 | complete | Stakeholders invested in new bill. Sponsors in place | these were forwarded to Rep Lee | Work with Pete Lee and Linda Newell. Set schedule for stakeholder meetings | Deb has started list and is in communication with Rep Lee
Develop MOU template | Committee with Pilots |  | done |  |  |  | Outline the process, agreements, protocols, distibution of funds, community partners, providers, eventually P&P, | Deb completed this using the SCAO legal department requirements

## Research
RJ COUNCIL ACTION PLANNING WORKSHEET
WORKGROUP: | Research
CHAIR: | Perrie Mc Millen
MEMBERS: | Candie, Rebecca, Spiro, Alice, Meg | Esther, Peggy, (not present at assignment) | Kerri Schmidt- Community Volunteer
Activity Task | Responsible Party | Projected Timeline | Completion Date | Outcomes | Communication | Next Steps | Notes | Updates from Meeting
Working Draft of Surveys | committee with research team | march 31 2014 | completed by Omni | available to pilots on cloud-based system | committee agrees to wait until researchers are able to contribute befroe finalizing | hire research team | RDQs are being scored and will be done Feb 21, 2014
Recidivsm- Review, Define and Present | committee with research team | 2014-06-30 | Council has working definition | ensure all pilots understand and are on same page with definition
Work with Contracted research team | Deb & committee | march 31 2014 | Omni was contracted
Statewide Evaluation | Deb | 2014-01-31 | done | report complete and sent to council, contributors and joint judiciary
meaningful statewide data collection system and 100% participation
Data from Pilots | pilots, deb, software and committee | on-going | Omni using ETO
Funding | deb, judicial and committee | 2014-06-30 |  | pilots will be able to do the work once they have funding

## Legislative Public Policy
RJ COUNCIL ACTION PLANNING WORKSHEET
WORKGROUP: | Legislative Public Policy |  |  | JOINT WORK WITH CCRJD
CHAIR: | Lynn Lee
MEMBERS: | Matt, Monica, Nancy, Spiro, Meg, Greg | Pete Lee, Linda Newell, | Eileen Hyatt- community volunteer
Activity Task | Responsible Party | Projected Timeline | Completion Date | Outcomes | Communication | Next Steps | Notes | Updates from Meeting
Prep for 2015 Legislative Session | Deb | Drafted by late Nov 2014 | done | draft for Pete to propose in 2015 session | Deb- focus group | set up and invite
Funding Increase/Sustainability | legislature | 2015-05-01 | aug 2015 ongoing | $ for RJ | $780,000 spending authority approved for FY '15 and FY '16 |  | nedd to prep for FY '17 starting in May 2015
DOC/DYC High Risk VOD post conviction | Monica/Spiro | asap | DOC complete | DYC is doing a trianing in 2015
Clean-up legislation | Pete and comm | 2015 leg session | in progress

## Education & Engagement
RJ COUNCIL ACTION PLANNING WORKSHEET
WORKGROUP: | Education & Engagement
CHAIR: | Greg Brown
MEMBERS: | Paula, Matt, Perrie, Spiro, | Esther (not in attendance) | Kerri Schmidt - community volunteer
Activity Task | Responsible Party | Projected Timeline | Completion Date | Outcomes | Communication | Next Steps | Notes | Updates from Meeting
2014 Trainings | Deb | March- Vic Awareness, June MI, Sept Culture, Nov HRVOD | complete | 4 trainings offered by council in 2014 | March Deb & Nancy - good feedback, MI June Anjali- good feedback | call for trainers | Sept Culture- good feedback HRVOD good feedback. All trainigs repeat in 2015
Present to Law Enforcement Coordinators | Nancy make intro |  | by end of 2014
Educate Defense attorneys
Prep for 2016 Conference
Definitions Document (on website, in all presentations) |  |  | complete |  | Deb started this, pilots contributed on google doc- in progress |  | Deb brings this doc to all presenations and has handed it out to CCRJD, pilots and Council. It is posted on the website
Presentation on Standards | Deb & Comm member | early sept | done | living doc updated |  |  | same as definitions doc. Was open for comment in sept. no cooments submitted
Presentation on High Risk VOD | Lynn & Monica | Oct/Nov | done | more trained fac | Monica is bring jon Wilson out and Lynn is planning to do additional trianing in Nov |  | Monice brought Jon Wilson. Monica and Lynn then collaborated to make sure Lynn's curricuum relfected Jon's. Lynn did her training with Monica and got good feedback
Present to Juvenile Parole Board | Deb, Spiro, Rebecca | APAI | complete
CO Collaborative justice Conference | Deb and Greg | conf in May | complete |  |  |  |  | Submitted

## Internal Capacity
RJ COUNCIL ACTION PLANNING WORKSHEET
WORKGROUP: | Internal Capacity
CHAIR: | Spiro Koinis
MEMBERS: | Lynn, Gabrielle | Esther (not in attendance)
Activity Task | Responsible Party | Projected Timeline | Completion Date | Outcomes | Communication | Next Steps | Notes | Updates from Meeting
Defining RJ/RCJ
Group language/talking points
Keep Council docs up to date
Membership
Communication
Financials | deb | ongoing | ongoing |  | Deb stays in touch with Linda Edwards at state and sends reports as she gets them | keep councl updated | Greg is managing the Summit Account

## Sheet6
RJ COUNCIL ACTION PLANNING WORKSHEET
WORKGROUP:
CHAIR:
MEMBERS:
Activity Task | Responsible Party | Projected Timeline | Completion Date | Outcomes | Communication | Next Steps | Notes | Updates from Meeting